## EOAT Inventory
Audit ID | Audit Date | Auditor | Plant/Area | Press/Machine # | Tool # | Robot Type | Robot Model/Controller | Part Family | Part Name/Description | Cleanroom/Non-Cleanroom | EOAT Type | EOAT Moves | Connection Type | Number of Parts Picked | # of Grippers | Gripper Type | Gripper Model | Gripper Size | Cup Type/Material | Cup Diameter/Size | Vacuum Generator Type | EOAT Vacuum Circuits | EOAT Pressure Circuits | EOAT Interchangeable Circuits | Sensors Present? | Sensor Type | Sensor Brand/Model | Vacuum Confirmation Present? | Part-Present Detection Present? | Electrical/Wiring Present? | Quick Disconnects Present? | Pneumatic Quick Disconnect Type | Electrical Quick Disconnect Type | Tubing Condition | Tubing Routing Notes | Cable Management Condition | Mounting Hardware Condition | EOAT Alignment Condition | Fastener/Locking Hardware Present? | Estimated EOAT Weight | Known Issues | Drop/Mis-Pick History | Maintenance Frequency | Cycle Time Concern? | Scrap/Quality Concern? | Changeover Difficulty | Spare Parts Identified? | Drawing/CAD Available? | BOM Available? | Process Binder Complete? | Photos Taken? | Photo Folder/Link | Status | Priority | Pilot Candidate? | Follow-Up Needed | Notes | Entry Type | Source Audit ID | Compatibility Source
AUD-20260518-001 | 2026-05-18 | Fake Intern | Molding | Press 101 | TOOL-A | Wittmann R9 | Wittmann R9 / R8 controller | Part family A | Vacuum EOAT family A sample | Non-cleanroom | Vacuum |  |  | 8 | N/A | N/A | N/A |  | Nitrile bellows cup | 20 mm | Venturi |  |  |  | Yes | Vacuum switch | SMC ZSE20 | Yes | Yes | Yes | Yes | Push-to-connect | M12 | Leaking | Tubing wear near wrist rotation. | Loose | Good | Needs verification | Yes |  | Vacuum loss; part drops; tubing wear | Recurring part drops on startup. | Weekly | Yes | Yes | Medium | Yes | Yes | Yes | Yes | Yes | 01_EOAT_Audit/Cell_Photos/Overall | Candidate for pilot | High | Yes | Yes | Known issue cell with strong pilot potential.
AUD-20260518-002 | 2026-05-18 | Fake Intern | Molding | Press 102 | TOOL-B | Engel Viper | Engel Viper 20 | Part family B | Gripper EOAT family B sample |  | Mechanical / Gripper |  |  |  | 2 | Single Pressure | MHZL2-10S | [7 empty] | Yes | Part-present sensor |  |  |  | Yes |  |  |  | Good |  | Good | Good | Good |  |  | Sensor failure during intermittent cable flex. |  | Monthly |  |  |  | Yes | No | No | No | No |  | Audited | Medium | Maybe | Yes | Missing documentation fields are intentional fake data.
AUD-20260518-003 | 2026-05-18 | Fake Intern | Molding | Press 103 | TOOL-C | Other | Hybrid robot | Part family C | Hybrid EOAT family C sample |  | Hybrid |  |  | 4 | 1 | Double Pressure | MHZL2-16D |  | Silicone flat cup | [5 empty] | Yes | Vacuum and part-present |  |  |  | Yes |  |  |  | Fair |  | Good | Good | Good |  |  | Cable management issue previously corrected. |  | Monthly |  |  |  | Yes | Yes | Yes | Yes | Yes |  | Audited | Low | No | No | Complete documentation control row.

## Issue Log
Issue ID | Date Found | Plant/Area | Press/Machine # | Robot Type | EOAT Type | Issue Category | Issue Description | Suspected Cause | Evidence/Observation | Impact | Severity | Frequency | Detectability | Temporary Fix | Recommended Permanent Fix | Assigned To | Status | Follow-Up Date | Notes
ISS-001 | 2026-05-18 | Molding | Press 101 | Wittmann R9 | Vacuum | Vacuum loss | Vacuum drops during robot transfer. | Worn cups and tubing leak | Audible leak and drop history. | Downtime and scrap | 8 | 7 | 4 | Replace cup | Standardize cup and tubing route | Maintenance | Open | 2026-05-21 | High RPN seed data.
ISS-002 | 2026-05-18 | Molding | Press 102 | Engel Viper | Mechanical gripper | Sensor failure | Part-present signal intermittent. | Cable flex near wrist | Signal dropout during cycle. | Mis-picks | [6 empty] | Open |  | Missing risk numbers are intentional.
ISS-003 | 2026-05-18 | Molding | Press 101 | Wittmann R9 | Vacuum | Tubing wear | Tubing rubs on bracket. |  |  |  | 5 | 6 | 5 |  |  |  | In progress

## KPI Baseline
KPI ID | Date | Plant/Area | Press/Machine # | Tool # | Part Family | EOAT Type | Downtime Minutes | EOAT-Related Downtime? | Part Drops | Mis-Picks | Scrap Quantity | Scrap Reason | Cycle Time | Maintenance Event Count | Maintenance Notes | Data Source | Notes
KPI-001 | 2026-05-18 | Molding | Press 101 | TOOL-A | Part family A | Vacuum | 42 | Yes | 9 | 3 | 14 | Part drops | 18.4 | 3 |  | Fake MES extract
KPI-002 | 2026-05-18 | Molding | Press 102 | TOOL-B | Part family B | Mechanical gripper | 17 | Yes | 1 | 7 | 4 |  | 21 | 2 |  | Fake shift notes
KPI-003 | 2026-05-18 |  | Press 103

## Interview Notes
Interview ID | Date | Person Interviewed | Role/Department | Shift | Plant/Area | Press/Machine # | Main Question/Topic | Notes | Known EOAT Issues Mentioned | Suggested Improvements | Follow-Up Needed | Follow-Up Owner
INT-001 | 2026-05-18 | Synthetic Technician | Maintenance | A | Molding | Press 101 | Vacuum EOAT recurring issues | Vacuum loss and tubing wear are repeat problems. | Vacuum loss; part drops; tubing wear | Standard tubing route and cup selection. | Yes | Fake Intern

## Pilot Candidates
Candidate ID | Date Added | Plant/Area | Press/Machine # | Robot Type | Tool # | Part Family | EOAT Type | Main Problem | Evidence | Estimated Impact | Ease of Implementation | Safety/Quality Risk | Required Parts/Resources | Expected KPI Improvement | Recommended Action | Approval Status | Notes
PILOT-001 | 2026-05-18 | Molding | Press 101 | Wittmann R9 | TOOL-A | Part family A | Vacuum | Vacuum loss and part drops | Issue log and KPI downtime | High | Medium | Medium | Vacuum cups, tubing, fittings | Reduce drops and downtime | Pilot standard vacuum-cup and tubing kit | Proposed | Intentionally strong candidate.

## FMEA Draft
FMEA ID | Plant/Area | Press/Machine # | EOAT Function | Failure Mode | Failure Effect | Potential Cause | Current Controls | Severity | Frequency | Detectability | RPN | Recommended Action | Owner | Target Completion Date | Status | Notes
FMEA-001 | Molding | Press 101 | Grip part by vacuum | Vacuum loss | Part drops | Worn cup or tubing leak | Operator visual check | 8 | 7 | 4 | 224 | Standardize cup/tubing PM interval | Maintenance |  | Open
FMEA-002 | Molding | Press 102 | Confirm part present | Sensor failure | Mis-pick | Cable flex | [8 empty] | Draft

## Action Items
Action ID | Date Added | Action Item | Related Cell/Press | Owner | Priority | Due Date | Status | Completion Date | Notes
ACT-001 | 2026-05-18 | Follow up on Press 101 tubing wear. | Press 101 | Fake Intern | High | 2026-05-21 | In progress |  | Carryover action item for morning plan.

## Photo Index
Photo ID | Date Taken | Plant/Area | Press/Machine # | EOAT Area Shown | Photo Filename | Folder Path | Description | Related Audit ID | Related Issue ID | Notes
PHO-20260518-001 | 2026-05-18 | Molding | Press 101 | Overall | Molding_Press101_EOAT_2026-05-18_Overall_001.png | 01_EOAT_Audit/Cell_Photos/Overall | Fake indexed photo. | AUD-20260518-001 |  | Seed row.

## Audit by Press
EOAT Audit by Press
Last refreshed: 2026-05-27 16:02 | [15 empty] | Generated view from EOAT Inventory
Audit ID | Date | Auditor | Plant/Area | Press/Machine # | Tool # | Robot Type | EOAT Type | EOAT Moves | Connection Type | Cleanroom/Non-Cleanroom | Status | Entry Type | Source Audit ID | Priority | Known Issues / Observations | Photo Link / Photo Count
Molding / Press 101 - 1 physical, 0 compatible, 1 total entry | [15 empty] | 1 physical / 0 compatible / 1 total
AUD-20260518-001 | 2026-05-18 | Fake Intern | Molding | Press 101 | TOOL-A | Wittmann R9 | Vacuum |  |  | Non-cleanroom | Candidate for pilot |  |  | High | Vacuum loss; part drops; tubing wear | 01_EOAT_Audit/Cell_Photos/Overall
Molding / Press 102 - 1 physical, 0 compatible, 1 total entry | [15 empty] | 1 physical / 0 compatible / 1 total
AUD-20260518-002 | 2026-05-18 | Fake Intern | Molding | Press 102 | TOOL-B | Engel Viper | Mechanical / Gripper |  |  |  | Audited |  |  | Medium | Sensor failure during intermittent cable flex.
Molding / Press 103 - 1 physical, 0 compatible, 1 total entry | [15 empty] | 1 physical / 0 compatible / 1 total
AUD-20260518-003 | 2026-05-18 | Fake Intern | Molding | Press 103 | TOOL-C | Other | Hybrid |  |  |  | Audited |  |  | Low | Cable management issue previously corrected.